## Gantt Chart - Manual End Date
Task Name | Task Detail | Role | Resources | Presenter | Start Date | End Date | Duration (Days) | Days Complete | Days Remaining | Percent Complete | Start Date in Number Form | 43010 | Use this number for the Minimum Bound of the Horizontal Axis to set the beginning of the chart.
D1 – Team Topic Presentation | Gantt Chart, Slack Setup, PowerPoint Outline | PM/QA | Diego Miranda |  | 2017-10-02 | 2017-10-08 | 6 | 6 | 0 | 100%
D1 – Team Topic Presentation | Powerpoint , Trelo Setup, Sample setup | Developer | Rascive Grant |  | 2017-10-02 | 2017-10-08 | 6 | 6 | 0 | 100%
D1 – Team Topic Presentation | Docker setup | Developer | Will Levine | Will Levine | 2017-10-02 | 2017-10-08 | 6 | 6 | 0 | 100%
D1 – Team Topic Presentation | Research | Developer/QA | Bijaya Rijal |  | 2017-10-02 | 2017-10-08 | 6 | 6 | 0 | 100%
D1 – Team Topic Presentation |  | QA/PM | Carl Ashie Annan |  | 2017-10-02 | 2017-10-08 | 6 | 6 | 0 | 100%
D1 – Team Topic Presentation |  | QA | Yousuf Imran |  | 2017-10-02 | 2017-10-08 | 6 | 6 | 0 | 100%
Project Status Report 1 |  |  | TEAM COLLABORATION |  | 2017-10-09 | 2017-10-15 | 6 | 6 | 0 | 100%
D2 – Team Technical Presentation | SoftwareStack | Developer | Rascive Grant | Rascive Grant | 2017-10-16 | 2017-10-22 | 6 | 6 | 0 | 100%
D2 – Team Technical Presentation | Architecture ,Use Case Diagram | Developer | Will Levine |  | 2017-10-16 | 2017-10-22 | 6 | 6 | 0 | 100%
D2 – Team Technical Presentation | Powerpoint Outline Gantt Chart | Developer/QA | Bijaya Rijal |  | 2017-10-16 | 2017-10-22 | 6 | 6 | 0 | 100%
D2 – Team Technical Presentation |  | QA/PM | Carl Ashie Annan | Carl Ashie Annan | 2017-10-16 | 2017-10-22 | 6 | 6 | 0 | 100%
D2 – Team Technical Presentation |  | QA | Yousuf Imran |  | 2017-10-16 | 2017-10-22 | 6 | 6 | 0 | 100%
Project Status Report 2 |  |  | TEAM COLLABORATION |  | 2017-10-23 | 2017-10-29 | 6 | 6 | 0 | 100%
Project Status Report 3 |  |  | TEAM COLLABORATION |  | 2017-10-30 | 2017-11-05 | 6 | 6 | 0 | 100%
D3 – Team Progress Report | Front End Developmet | Developer | Rascive Grant |  | 2017-11-06 | 2017-11-12 | 6 | 6 | 0 | 100%
D3 – Team Progress Report | BackEnd Development | Developer | Will Levine |  | 2017-11-06 | 2017-11-12 | 6 | 6 | 0 | 100%
D3 – Team Progress Report | Powerpoint Outline Gantt Chart , Document | Developer/QA | Bijaya Rijal | Bijaya Rijal | 2017-11-06 | 2017-11-12 | 6 | 6 | 0 | 100%
D3 – Team Progress Report |  | QA/PM | Carl Ashie Annan |  | 2017-11-06 | 2017-11-12 | 6 | 6 | 0 | 100%
D3 – Team Progress Report |  | QA | Yousuf Imran |  | 2017-11-06 | 2017-11-12 | 6 | 6 | 0 | 100%
Project Status Report 4 |  |  | TEAM COLLABORATION |  | 2017-11-13 | 2017-11-19 | 6 | 6 | 0 | 100%
Project Status Report 5 |  |  | TEAM COLLABORATION |  | 2017-11-20 | 2017-11-26 | 6 | 6 | 0 | 100%
D4 – Team Final Project Presentation | Front End Developmet | Developer | Rascive Grant |  | 2017-11-27 | 2017-12-03 | 6 | 6 | 0 | 100%
D4 – Team Final Project Presentation | BackEnd Development | Developer | Will Levine | Will Levine | 2017-11-27 | 2017-12-03 | 6 | 6 | 0 | 100%
D4 – Team Final Project Presentation | Powerpoint Outline Gantt Chart , Document | Developer/QA | Bijaya Rijal |  | 2017-11-27 | 2017-12-03 | 6 | 6 | 0 | 100%
D4 – Team Final Project Presentation | Test | QA/PM | Carl Ashie Annan |  | 2017-11-27 | 2017-12-03 | 6 | 6 | 0 | 100%
D4 – Team Final Project Presentation | Test | QA | Yousuf Imran |  | 2017-11-27 | 2017-12-03 | 6 | 6 | 0 | 100%
D5 – Team Final Project | Front End Developmet | Developer | Rascive Grant |  | 2017-11-27 | 2017-12-03 | 6 | 6 | 0 | 100%
D5 – Team Final Project | BackEnd Development | Developer | Will Levine |  | 2017-11-27 | 2017-12-03 | 6 | 6 | 0 | 100%
D5 – Team Final Project | Final Delivery Docs, Gantt Chart , Test | Developer/QA | Bijaya Rijal |  | 2017-11-27 | 2017-12-03 | 6 | 6 | 0 | 100%
D5 – Team Final Project | Test | QA/PM | Carl Ashie Annan |  | 2017-11-27 | 2017-12-03 | 6 | 6 | 0 | 100%
D5 – Team Final Project | Test | QA | Yousuf Imran |  | 2017-11-27 | 2017-12-03 | 6 | 6 | 0 | 100%
Team Evaluation |  |  | COMPLETED INDIVIDUALLY |  | 2017-12-04 | 2017-12-10 | 6 | 0 | 6 | 0%